## Sheet1
Requirment ID | Description | Story Points | Priority(1-5) | Sprint #
1 | Securely install LiDAR sensor at garage entry/exit for reliable detection | 5 | 1 | 3
2 | Communicate between Raspberry Pi and LiDAR sensor over UART or I2C | 8 | 1 | 3
3 | Read LiDAR distance measurements at a configurable sampling rate | 8 | 1 | 3
4 | Log continuous LiDAR readings for 10 minutes without crashing | 5 | 1 | 4
6 | Filter LiDAR noise to prevent false vehicle triggers | 8 | 2 | 3
7 | Classify detected events as ENTRY or EXIT using sensor placement and direction logic | 13 | 1 | 3
8 | Achieve at least 95% ENTRY/EXIT classification accuracy in controlled testing | 5 | 2 | 4
9 | Prevent duplicate events using debounce or cooldown logic | 5 | 3 | 2
10 | Define a JSON schema for all occupancy update payloads | 5 | 1 | 2
11 | Send occupancy updates via authenticated HTTP POST requests from the Raspberry Pi | 3 | 2 | 3
12 | Validate incoming requests with a Cloud Function before writing to Firebase | 5 | 1 | 2
13 | Reject unauthorized or malformed requests with clear error responses | 2 | 1 | 2
14 | Store all parking and event data with server-side timestamps | 8 | 1 | 2
15 | Implement Firebase-backed endpoint /event/entry to record entry events | 5 | 1 | 1
16 | Implement Firebase-backed endpoint /event/exit to record exit events | 5 | 1 | 1
17 | Write each detected entry/exit event to Firebase as an immutable event record | 3 | 1 | 1
18 | Include unique ID, timestamp,, and eventType in each event record | 2 | 2 | 1
19 | Update garage occupancy count based on entry/exit events | 8 | 2 | 1
20.1 | Interpret natural-language parking queries in the chatbot based on real time data | 13 | 1 | 1
20.2 | Respond to chatbot parking queries within 2 seconds under load | 8 | 2 | 3
21 | Enforce occupancy limits (0 ≤ occupancy ≤ capacity) | 5 | 1 | 2
22 | Retrieve real-time occupancy updates in the web app within 1–3 seconds | 8 | 1 | 2
23 | Display sensor online/offline status and last-updated timestamp in the app | 5 | 2 | 4
24 | Display occupancy percentage and availability state (Low/Medium/High/Full) in the app | 5 | 2 | 3
25 | Trigger a near-full alert when occupancy exceeds a configurable threshold | 5 | 2 | 5
26 | Pull event data into the calendar from the KU events page | 5 | 3 | 5
27 | Ensure color-blind accessibility and readable text contrast for all UI elements | 3 | 5 | 5
28 | Display a loading indicator in the web app while occupancy data is being fetched | 1 | 4 | 1
29 | Show a fallback message when real-time parking data is unavailable | 1 | 4 | 5
30 | Log basic system startup and shutdown events for the sensor service | 2 | 4 | 4
31 | Improve current dark mode on website to make more readable | 3 | 1 | 1
32 | Make website responsive to different screen sizes | 3 | 2 | 1
33 | Host web server on firebase | 8 | 2 | 2
34 | Include pre-written suggested prompt to ask the chatbot | 3 | 4 | 2
35 | Implement a Firebase-backed authenticated GET endpoint that allows the web application to retrieve real-time occupancy data. | 8 | 1 | 2
36 | Ensure the website fetches occupancy data from the Firebase GET endpoint instead of using mock data. | 5 | 1 | 2